## Project tracker
Project tracker
[7 empty] | Q1 | [14 empty] | Q2 | [14 empty] | Q3 | [14 empty] | Q4
TASK | TASK | TASK | START | DUE | DURATION | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
ID | TITLE | OWNER | DATE | DATE | IN DAYS | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Project Charter | Jonathan | 2022-08-01 | 2022-08-27 | 26 | 100%
1.1.1 | Check prerequisites | Jonathan | 2022-08-01 | 2022-08-27 | 26 | 100%
1.2 | Setup and configure github,azure | Jonathan | 2022-08-01 | 2022-08-27 | 26 | 100%
1.3 | Projections | Jonathan | 2022-08-01 |  | -44774 | 100%
1.4 | Stakeholders | Jonathan | 2022-08-01 |  | -44774 | 100%
1.5 | Guidelines | Jonathan | 2022-08-01 |  | -44774 | 100%
1.6 | Project Initiation | Jonathan | 2022-08-01 |  | -44774 | 100%
2 | Project Definition and Planning |  |  |  |  | 100%
2.1 | Scope & Goal Setting | Jonathan | 2022-08-01 |  | -44774 | 100%
2.2 | Budget | Jonathan | 2022-08-01 |  | -44774 | 100%
2.3 | Communication Plan | Jonathan | 2022-08-01 |  | -44774 | 100%
2.4 | Risk Management | Jonathan | 2022-08-01 | 2022-08-27 | 26 | 100%
3 | Continuous Integration |  |  |  |  | 100%
3.1 | Review status, update tracker | Jonathan | 2022-08-01 | 2022-08-27 | 26 | 100%
3.2 | Add starter files + scaffolding | Jonathan | 2022-08-01 | 2022-08-27 | 26 | 100%
3.2.1 | Add install, lint, tests to makefile | Jonathan | 2022-08-01 | 2022-08-27 | 26 | 100%
3.2.2 | Run ML app predict and API | Jonathan | 2022-08-01 | 2022-08-27 | 26 | 100%
3.3 | Setup app service in azure | Jonathan | 2022-08-01 | 2022-08-27 | 26 | 100%
3.3.1 | Run gh actions and workflow | Jonathan | 2022-08-01 | 2022-08-27 | 26 | 100%
4 | Continuous deployment / Monitoring |  |  |  |  | 100%
4.1 | Create azure devops project | Jonathan | 2022-08-01 | 2022-08-27 | 26 | 100%
4.2 | Create service connection, pipelines | Jonathan | 2022-08-01 | 2022-08-27 | 26 | 100%
4.3 | Run end to end CI-CI pipelines | Jonathan | 2022-08-01 | 2022-08-27 | 26 | 100%
4.4 | Review and submit project | Jonathan | 2022-08-01 | 2022-08-27 | 26 | 100%